## Example
Introduction: Welcome to the Community Benefit Tracker. This tracking tool was created to help your facility track the progress of your Community Benefit Implementation Plan. Additionally, the tracker will assist in the project management, 990 reporting, and evaluation and impact of your implementation plan activities. Instructions: 1) The Montana Office of Rural Health has pre-populated each sheet of this excel document with the information from your most current Implementation Plan Report. 2) Revisit the tracker and your implementation plan quarterly/semi annually, and use the drop down options to report your progress on each of the activities. Progress will automatically be updated on the 'Executive Summary' sheet/tab. 3) Use the 'accomplishments' and 'barriers' sections to report your tracking measures- successes or barriers encountered with each activity. 4) The 'Community Impact/Outcomes from activities' section can be used to report any observed or anticipated impact from the activity. 5) Use the 'Cost/resources sections' to track expenses that can be reported on your annual 990 tax form. 6) Each strategy includes a 'propposed measure of success' (bottom of sheet/tab), indicate how you will track this success and include a narrative update on your progress. *See example below of how to use the tracker. Contact Amy Royer with MORH with any questions or suggestions at amy.royer@montana.edu
COMMUNITY BENEFIT IMPLEMENTATION PROGRESS TRACKER - Hospital Name, Town, MT Please refer to Community Health Needs Assessment (CHNA) and Implementation Plan (IP) completed: DATE 2019
GOAL |  | STRATEGY | ACTIVITIES | Responsibility | Due Date/Date of Event | Partners | FY 2019 |  |  |  | FY 2020 |  |  |  | FY 2021 |  |  |  | ACCOMPLISHMENTS | BARRIERS | COMMUNITY IMPACT/ OUTCOMES from activities | Cost/resources associated with activity (for 990 tax reporting)
Complete - C
In Progress - P
No Progress (see barriers) - X
[7 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
1 | Goal 1: Improve access to healthcare services | 1.1: Increase access to primary care services | Conduct feasibility study of expanded clinic hours | Clinic Manager | 2020-02-01 | [13 empty] | Feasibility study was conducted and provider schedules were staggered to add 2 additional appointment hours to each day |  | Expanded primary care access | bar: No Progress (see barriers) - X Q3
|  |  | Evaluate impact of expanded hours (time, appointments, workforce, and pharmacy) and make adjustments as necessary. | Clinic Manager | 2020-02-01 | [14 empty] | Workforce shortage in pharmacy has led to a mismatch in hours with the clinic | bar: No Progress (see barriers) - X Q3
|  |  | Continue efforts to recruit a physician to expand service availability | CEO | Ongoing | AHEC Recruitment Program/3RNet/MHN/Montana Hospital Jobs | [12 empty] | Recount recruitment efforts* | bar: No Progress (see barriers) - X Q3
|  |  | Create marketing /education outreach on services that Advanced Practice Providers can provide and educate on how facility is working to expand desired primary care services | Marketing | Ongoing | [14 empty] | Turnover in the marketing department has halted progress. Will revisit once a new marketing director is hired | Community awareness of the qualifications and quality of Advanced Practice Providers is improved | bar: No Progress (see barriers) - X Q3
| Proposed Measures of Success: |  |  | How are the measures tracked? |  |  | No Progress (see barriers) - X Q1: Update on Measures of Success | Other Comments regarding Goal 1:
1.1 | With the expansion of clinic hours/and or the addition of a new primary care provider, the clinic is able to see 15% more patients a year |  |  | Number of patients seen prior to expanded clinic hours Number of patients seen at the end of each fiscal year after expansion of hours/new provider |  |  | No Progress (see barriers) - X Q1: x patients were seen in the clinic in 2018 After expanded hours were implemented, X patients were seen at the clinic in 2019. As of year two of the IP plan, 10% more patients were seen at the clinic. | Senior management met on 3/03/2020 to the review the IP report and update on progress. Next meeting in scheduled for 7/06/2020.

## Goal 1
COMMUNITY BENEFIT IMPLEMENTATION PROGRESS TRACKER - Pondera Medical Center, Conrad, MT Please refer to Community Health Needs Assessment (CHNA) and Implementation Plan (IP) completed: December 2019
GOAL |  | STRATEGY | ACTIVITIES | Responsibility | Due Date/Date of Event | Partners | FY 2019 |  |  |  | FY 2020 |  |  |  | FY 2021 |  |  |  | ACCOMPLISHMENTS | BARRIERS | COMMUNITY IMPACT/ OUTCOMES from activities | Cost/resources associated with activity (for 990 tax reporting)
Complete - C
In Progress - P
No Progress (see barriers) - X
[7 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
1 | Goal 1:Enhance access to healthcare services in Pondera County. | 1.1: Improve access to primary care services at PMC | Consider alternative staffing models to best meet community appointment needs | RHC Manager Medical Staff | 2020
|  |  | Include new questions regarding point of care needs as a part of patient satisfaction survey | RHC Manager Marketing | 2020
|  |  | Consider expanding/adjusting primary care hours | RHC Manager | 2021
|  |  | Create outreach materials to educate community on provider scope of practice | RHC Manager Marketing | 2020
|  |  | Create outreach opportunities to introduce PMC’s provider team to community (providers scope, interests, and patient testimonials, etc.) | RHC Manager Marketing | 2020 | Chamber of Commerce, Pondera Center
|  |  | Develop outreach materials to educate community on how to access the most appropriate level of care (ED vs. walk-in vs. clinic appointment) | RHC Manager Marketing | 2020
|  | 1.2: Improve access to specialty care services at PMC | Create outreach materials to educate community on specialty provider services, introduction to specialty providers and availability | RHC Manager Marketing | 2020 | Local newspapers, KSEN radio
|  |  | Explore enhancing specialty services at PMC onsite or via telehealth (cardiology, urology, dermatology) | RHC Manager CEO | 2021 | KRH, Benefis, University of Utah, UCHealth
|  | 1.3: Explore new modalities to enhance PMC’s outreach and communication | Explore alternative methods to provide outreach (via short wave radio, social media (live), podcast, utilization of facility monitors, electronic billboard, etc.) | CEO, HR, Marketing | 2022 | KRH, Local radio stations
|  |  | Reach out to community partners to assess community resources and opportunities to disseminate/share services/information | Marketing | 2021 | PCHD, Mental Health Advisory, Chamber of Commerce
|  |  | Continue to refer patients to, and provide outreach to educate community on insurance navigation, cost assistance programs etc. | Marketing, Director of Finance | 2021 | DPHHS, N. Central Council on Aging, PCHD, MSU Extension
|  |  | Continue to foster youth engagement through various outreach programs by leveraging programs/events such as National Rural Health Day, REACH, CNA trainings, etc. | Marketing, Human Resources, CNO | 2022 | MT AHEC, MHN, Conrad School District, MHA
| Proposed Measures of Success: |  |  | How are the measures tracked? |  |  | No Progress (see barriers) - X Q1: Update on Measures of Success | Other Comments regarding Goal 1:
1.1 | PMC expands access to primary care services by determining the best staffing and hours of operation in the clinic by 01/2021.
1.2 | PMC sees an increase in telehealth visits and number of specialty providers.
1.3 | All community health and wellness resources and programs are published and marketed by PMC to community by 1/2022 using different marketing platforms.

## Goal 2
COMMUNITY BENEFIT IMPLEMENTATION PROGRESS TRACKER
GOAL |  | STRATEGY | ACTIVITIES | Responsibility | Due Date/Date of Event | Partners | FY 2019 |  |  |  | FY 2020 |  |  |  | FY 2021 |  |  |  | ACCOMPLISHMENTS | BARRIERS | COMMUNITY IMPACT/ OUTCOMES from activities | Cost/resources associated with activity (for 990 tax reporting)
Complete - C
In Progress - P
No Progress (see barriers) - X
[7 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
2 | Goal 2: Enhance PMC’s chronic care management and prevention efforts to reduce chronic disease burden. | 2.1: Host or sponsor community events that promote prevention and wellness | Continue to host annual health fair (providing reduced rate laboratory screenings, health education, services and resources) | Management Council | Ongoing | PCHD, MSU Extension, Benefis, KRH
|  |  | Host/sponsor community events (Community Fun Run, Golf Tourney, Ghost Out, Community Wellness Challenges, National Night Out etc.) | Marketing, Wellness Committee, Management Council | Ongoing | Local law enforcement, Chamber of Commerce, PCHD
|  |  | Explore developing a youth/family wellness programs (New Year challenge, Steps challenge, Physical Therapy lectures, etc.) | Rehab Services, Marketing, Wellness Committee | 2020 | Conrad School District, PCHD
|  | 2.2: Enhance chronic care management services and resources at PMC | Implement PMC chronic care management program | RHC Manager, RHC | 2020 | Healthtechs, CMC
|  |  | Develop internal protocols to determine eligible patient population | RHC Manager, Medical Staff | 2020 | Healthtechs, CMC
|  |  | Create outreach materials to invite potential participants | RHC Manager, Marketing | 2020 | Healthtechs, CMC
|  | 2.3: Enhance health educational offerings available through PMC | Convene staff team to develop and spearhead health and wellness resources/ opportunities/ partners | Management Council | 2022 | PCHD, MSU Extension, Pondera Healthcare Foundation
|  |  | Explore development of health education series o Women’s health o Fitness and nutrition o Prevention and screenings | RHC Manager, Medical Staff, Marketing, Dietary services, Rehab | 2021 | PCHD, Conrad Fitness Club
|  |  | Determine new modalities to engage and disseminate health and resource series (videos on website, Facebook, presentations, etc.) | Marketing, Management Council | 2022 | KRH, Local radio station, Local newspapers
| Proposed Measures of Success: |  |  | How are the measures tracked? |  |  | No Progress (see barriers) - X Q1: Update on Measures of Success | Other Comments regarding Goal 2:
2.1 | PMC sees an increase in community engagement in facility sponsored events.
2.2 | PMC Improves care transitions and reduces readmissions.
2.3 | PMC engages with community through social media monthly.

## Goal 3
COMMUNITY BENEFIT IMPLEMENTATION PROGRESS TRACKER
GOAL |  | STRATEGY | ACTIVITIES | Responsibility | Due Date/Date of Event | Partners | FY 2019 |  |  |  | FY 2020 |  |  |  | FY 2021 |  |  |  | ACCOMPLISHMENTS | BARRIERS | COMMUNITY IMPACT/ OUTCOMES from activities | Cost/resources associated with activity (for 990 tax reporting)
Complete - C
In Progress - P
No Progress (see barriers) - X
[7 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
3 | Goal 3: Enhance mental and behavioral health services in Pondera County. | 3.1: Continue to promote and provide behavioral health resources in Pondera County | Continue to participate in various community programs that address mental health in Pondera County (Pondera County Mental Health Advisory Board, Mental Health Consortium, DUI Task Force) | RHC Manager, EMS Manager, CNO | Ongoing | Pondera County Mental Health Advisory Board, Mental Health Consortium, DUI Task Force
|  |  | Continue to participate in Integrated Behavioral Health and Opioid grant projects enhancing behavioral health services at PMC | RHC Manager | Ongoing | NMHA
|  |  | Continue to research/seek behavioral health services, resources, grants, staff and community partner skill development opportunities (MOAB, Mental Health First Aid, etc.) | Management Council | Ongoing | MT AHEC, DPHHS, NMHA, MHA
|  |  | Create web-based calendar and information of available local and state mental health resources | Marketing | 2020 | Local and state mental health resources
| Proposed Measures of Success: |  |  | How are the measures tracked? |  |  | No Progress (see barriers) - X Q1: Update on Measures of Success | Other Comments regarding Goal 3:
3.1 | PMC continues partnership with community programs and adds additional community events.

## Executive Summary
Executive Summary |  |  | FY 2019 |  |  |  | FY 2020 |  |  |  | FY 2021
Complete - C
In Progress - P
*This page is automatically populated by filling out your activity progress on each goal page* |  |  | No Progress (see barriers) - X
Goal 1 | Strategy | Activity | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Goal 1:Enhance access to healthcare services in Pondera County. | 1.1: Improve access to primary care services at PMC | Consider alternative staffing models to best meet community appointment needs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Include new questions regarding point of care needs as a part of patient satisfaction survey | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Consider expanding/adjusting primary care hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Create outreach materials to educate community on provider scope of practice | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Create outreach opportunities to introduce PMC’s provider team to community (providers scope, interests, and patient testimonials, etc.) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Develop outreach materials to educate community on how to access the most appropriate level of care (ED vs. walk-in vs. clinic appointment) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2: Improve access to specialty care services at PMC | Create outreach materials to educate community on specialty provider services, introduction to specialty providers and availability | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Explore enhancing specialty services at PMC onsite or via telehealth (cardiology, urology, dermatology) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3: Explore new modalities to enhance PMC’s outreach and communication | Explore alternative methods to provide outreach (via short wave radio, social media (live), podcast, utilization of facility monitors, electronic billboard, etc.) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reach out to community partners to assess community resources and opportunities to disseminate/share services/information | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Continue to refer patients to, and provide outreach to educate community on insurance navigation, cost assistance programs etc. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Continue to foster youth engagement through various outreach programs by leveraging programs/events such as National Rural Health Day, REACH, CNA trainings, etc. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Goal 2: Enhance PMC’s chronic care management and prevention efforts to reduce chronic disease burden. | 2.1: Host or sponsor community events that promote prevention and wellness | Continue to host annual health fair (providing reduced rate laboratory screenings, health education, services and resources) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Host/sponsor community events (Community Fun Run, Golf Tourney, Ghost Out, Community Wellness Challenges, National Night Out etc.) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Explore developing a youth/family wellness programs (New Year challenge, Steps challenge, Physical Therapy lectures, etc.) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.2: Enhance chronic care management services and resources at PMC | Implement PMC chronic care management program | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Develop internal protocols to determine eligible patient population | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Create outreach materials to invite potential participants | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.3: Enhance health educational offerings available through PMC | Convene staff team to develop and spearhead health and wellness resources/ opportunities/ partners | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Explore development of health education series o Women’s health o Fitness and nutrition o Prevention and screenings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Determine new modalities to engage and disseminate health and resource series (videos on website, Facebook, presentations, etc.) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Goal 3: Enhance mental and behavioral health services in Pondera County. | 3.1: Continue to promote and provide behavioral health resources in Pondera County | Continue to participate in various community programs that address mental health in Pondera County (Pondera County Mental Health Advisory Board, Mental Health Consortium, DUI Task Force) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Continue to participate in Integrated Behavioral Health and Opioid grant projects enhancing behavioral health services at PMC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Continue to research/seek behavioral health services, resources, grants, staff and community partner skill development opportunities (MOAB, Mental Health First Aid, etc.) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Create web-based calendar and information of available local and state mental health resources | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sheet5 (hidden)
C
P
X